## Slide 1: FastTrack for Dynamics 365
<NAME>
<Job Title>
Cutover Strategy Workshop
Created On: dd/MM/yyyy

## Slide 2: Cutover Strategy Workshop Agenda
Agenda
The Cutover Strategy workshop is designed to help ensure that the project team has a good approach and a realistic plan to deliver a well-defined, well-tested, and reliable transition from current systems to Dynamics 365 application(s)..
Cutover Vision & Strategy
Cutover Project Plan
Go-Live Cutover Plan
Post Go-Live Plan
Format: 120-minute Microsoft Teams call
Attendees: Cutover Lead, Solution Architect, Data Migration Lead and Project Manager roles are mandatory.
Other roles that may attend are Technical Leads and Functional Leads
Q/A & Next Steps

## Slide 3: Cutover Vision & Strategy

## Slide 4: Business Aims & Goals
Describe the aims or goals of the cutover from a business perspective (include business constraints such as the maximum duration for system shutdown and any other business disruption for cutover)
Enter Details Here
Customer slide (please update)
Who is the designated cutover leader and what is the scope of their responsibilities?
Add Info Here
Describe the responsibilities and ownership of the key cutover activities (like data cleansing, data migration, communication, etc)?
Add Info Here
Notes: Notes to help complete this slide:
The business aims and goals for cutover are the underlying principles and requirements from the business perspective. These are normally expressed in broader business terms and derived from the existing project scope, but focused on the cutover-specific requirements:
  Which end-to-end business processes need to transition to the new system (this may reference the project scope) and any specific cutover-related requirements and constraints
  The types (logical data entities) and range of data (e.g. customers that have placed order in the last 12 months) that needs to be moved from legacy systems
  Data and system requirements during the project (e.g. for testing, training etc)
  Any specific requirements from the business on the cutover processes
  How will the business operate during the shutdown period?
  The maximum system shutdown period that the business is able to sustain during the cutover process
  The periods when the cutover cannot be done (for example not close to some critical business events such as Christmas for retail organizations)
  Any specific constraints on the business activities leading up to the cutover. For example, “the systems needed for the customer call centre must be available on all weekdays between 08:00 – 18:00 local time”, or “there can be no disruption to the customer-facing commerce website for more than 4 hours”, etc
  Cutover Leader:
  Having a cutover leader that has overall accountability for the design and delivery of cutover provides a single vision for the cutover requirements and design,and help coordinate across the various teams that need to participate in the delivery. The cutover Leader would typically coordinate:
  business teams for requirements on data cleansing, data quality, regulatory requirements, data validation etc
  data migration team for all tasks related to moving the data
  technical teams for requirements for environments for D365, for any test environments for legacy system
  technical teams for requirements for integrations (before cutover for testing, during cutover and after cutover) etc,
  change management
  Etc
  However, projects will have different project organizational structures and it is important to understand the extent and scope of the responsibilities of the cutover leader and other key roles.

## Slide 5: Cutover Scope & Strategy
Describe the full scope that is intended to be covered by the cutover
Enter Details Here
Customer slide (please update)
Describe the high-level strategy for the cutover
Enter Details Here
Notes: Full scope of the cutover should describe the set of requirements to transition system, data, process and people from current systems to Dynamics 365
The cutover strategy should address how the transition will be designed and delivered. For example, will the data be moved as a single “big bang” during the final cutover to Go Live, or will master data (and other slow-moving data) be moved a few days before and only the changes and any remaining data moved during the final Go Live cutover. What will be the strategy to deal with data cleansing in the source data? What will be the strategy for validating the data in transit and the migrated data? How will moving system integrations be managed? What will be the related strategy to manage the transition of processes? Etc.
Typically, a cutover strategy would consider the following as a minimum:
Scope, Requirements and Dependencies
Roles and responsibilities
Business calendar activities (not just data migration)
High-level cutover project plan with mock cutovers
Initial detailed Go-Live cutover plan (including fallback plan and rules)
Reconciliations – what’s needed and how done, source data cleaning toolkit etc
Environment management plan
Assess impact on business ecosystem and identify other owners
Etc

## Slide 6: Cutover Calendar
Describe the calendar of key business activities that will take place leading to, and during the cutover.
Enter Details Here
Customer slide (please update)
Notes: The cutover calendar should highlight the key business processes that the business needs to conduct around the Go-Live that may impact cutover.
The high-level technical cutover tasks and milestones can then be overlaid on the key business process milestones to ensure these are aligned.
Typically, the cutover calendar needs to show a single overall view and then a more detailed view per major end-to-end process area (for example, “Quote to Cash” or “Procure to Pay” etc or by major function such as “Finance” or “SCM”etc.).

## Slide 7: Cutover Project Plan

## Slide 8: High-level Cutover Project Plan
Please describe and include a copy of your cutover project plan.
Enter Details Here
Customer slide (please update)
Notes: Show the high-level cutover plan in the context of overall project plan. For example, some of the key milestones for the cutover process:
Definition and approval of the cutover strategy
Definition and approval of the cutover business calendar
Key data migration milestones (scope agreed, design agreed, key incremental data readiness stage gates etc)
Key mock cutovers (for example, prior to major test phases such as System Integration Testing or User Acceptance Testing)
Final mock cutover (in Production?)
Go Live cutover
etc.

## Slide 9: Data Cutover
What are the Data Migration processes (and milestones) that are managed by, or integrated with, the cutover management process?
How many data migration runs (as part of the mock cutover) have been completed and with what level of success ?
Add Info Here – Reference the Data Migration Strategy/Workshop as needed.
Add Info Here – Reference the Data Migration Strategy/Workshop as needed.
What is the detailed Data Cutover strategy?
Customer slide (please update)
Add Info Here
Notes: Data Cutover
If all the above is covered by the Data Migration Strategy and/or plan, reference the relevant sections
For the details on the data migration practice/mock runs, also define the time taken end-to-end so the progress towards being ready to run this for the Go Live cutover can be assessed.

## Slide 10: System Cutover
What are the system cutover processes (and milestones) that are managed by, or integrated with, the cutover management process?
Add Info Here – Reference the Data Migration Strategy/Workshop as needed.
Add Info Here – Reference the Data Migration Strategy/Workshop as needed.
What is the detailed system cutover strategy including the agreed legacy system shutdown process with the date and times?
Customer slide (please update)
Notes: System Cutover
If all the above is covered by the cutover strategy/ cutover plan or some other document, reference the relevant sections

## Slide 11: Testing & Mock-Cutovers
What are the entry/exit criteria for mock cutovers?
Add Info Here
How, when and where are the mock cutovers conducted and how are you validating the cutover process and the resulting systems?
Add Info Here
Customer slide (please update)

## Slide 12: Timing & Performance
How long is the final end-to-end cutover expected to take?
What day and time will the final cutover start and when is the new system expected to be live?
Add Info Here
Add Info Here
What are the high-risk areas for performance during the cutover and how are they being addressed?
Add Info Here
Customer slide (please update)

## Slide 13: Change Management
Describe how change management has been implemented and communicated with the business users throughout the project as it relates to the implications of the cutover strategy.
Add Info Here
Customer slide (please update)

## Slide 14: Environment Plan – Human Resources
Which environment is currently used as the GOLD environment?
What is the strategy to move from GOLD to PROD?
Add Info Here
Add Info Here
Describe the environment strategy for the mock go-lives.
Add Info Here
Customer slide (please update)

## Slide 15: Environment Plan – F&O
Which environment is currently used as the GOLD environment?
What is the strategy to move from GOLD to PROD?
Add Info Here
Add Info Here
Describe the environment strategy for the mock go-lives.
Add Info Here
Customer slide (please update)

## Slide 16: Environment Plan – CE
Which environment(s) will be used to support the mock go-live activities?
Add Info Here
Add Info Here
Describe the environment strategy for the mock go-live.
Customer slide (please update)

## Slide 17: Go-Live Cutover Plan

## Slide 18: Go-Live Cutover Organization
Describe the organizational structure that will manage, perform, validate and approve the final Go-Live cutover and the related communication plan
Enter Details Here
Customer slide (please update)

## Slide 19: Final Go-Live Detailed Cutover Plan
Describe the key elements of the Go-Live cutover plan and attach a copy of the current draft here
Enter Details Here
Customer slide (please update)

## Slide 20: Go/No-Go & Rollback Plans
Describe the Go/No-Go decision points and when they will be made
Enter Details Here
Customer slide (please update)
Describe the criteria for invoking rollback and/or contingency and the plans for executing them
Enter Details Here

## Slide 21: Remote Go-Live – Key Considerations
Communication – Organization
Communication – People
Communication – Strategy and technology
Communication, Communication, Communication
Notes: Main Additional Risks to Manage:
Easy to underestimate the impact of the remote Go-Live!
Behavior & level of engagement changes when working remotely
Unclear communication channels
Unclear communication patterns
Unclear rules of engagement
Hermits, ghosts and “squeaky wheels”
Decentralized process ownership  lack of control
Over-centralized ownership  lack of reactivity and effectiveness
Technical issues
Human factors

## Slide 22: Communication Plan Strategy Example
Coordinator
Stream/area leaders
Task owners
Issues manager
The coordinator runs the process
The area leaders verify the task execution and unblock issues (decision makers)
Task owners execute the tasks
Issue manager coordinates problems resolution in parallel with the “normal” execution

## Slide 23: Remote Go-Live Considerations
How is the cutover management strategy being designed to work effectively and efficiently for a Remote Go-Live?
Add Info Here
Customer slide (please update)
Notes: For remote Go Live tasks need to be:
    more detailed and more precise
    better definition of the responsibility
    push for a buddy system where possible, as hard for individuals to take the burden otherwise
Tasks for business users need to be especially carefully prepared with the principles above in mind
Increase the buffer between key stages to give you more reliability for those who only have a few (key) tasks to perform.
Have a “cutover Go Live board” or shared Excel which everyone can view, but only editable by the cutover organizer (and substitute).
Set more frequent and specific team review gates
Ownership and organization
There must be a strong coordinator to run the whole process.
Responsibilities defined for everyone
    Leaders for each area of the cutover to ensure “expert” coordination and decision making
    Responsibility for each task assigned to a specific person
    Need to explicitly secure availability, especially for business users and key partner resources
Appoint an area-level issue manager/leader
    Area-level issue board with recurring update
    Map all the issues to some cutover task to ensure traceability and dependences are clear
    Avoid area-level issues from blocking the whole cutover or dragging everyone into the discussion
Double-check agreements by all stakeholders for business and system blackout and business involvement
Technical preparation
Provide training on remote tools (Teams, RDP, etc) and ensure they are working prior to the cutover, especially for non-technical people
Validation of remote access communications (Teams – Screen share etc..) with defined backups (e.g. teleconference phone, SMS etc)
Validation for data access (VPNs, Firewalls, credentials etc)
Consider if someone with admin access needs to be on-site for any legacy systems access or emergencies
Internet connection and bandwidth for everyone
Security/Regulations: can data leave the premises where/if needed?
Human factor
Buddy system where possible
Efficiency improvement – avoid unwritten or untold microtasks
High task granularity helps to control and allows handovers

## Slide 24: Post Go-Live

## Slide 25: Post Go-Live Activities
Describe the process and planning for transition from project to support (esp with respect to the cutover and immediate hyper care period)
Enter Details Here
Customer slide (please update)
Describe any post Go-Live cutover activities and how they will be managed
Enter Details Here
Describe the exit criteria and strategy for the cutover process and cutover organization
Enter Details Here
Notes: Many cutovers do not end when the system goes live. There may be activities that need to be conducted after the Go Live, both in the new Dynamics 365 application, but also in the legacy system.
Consider what those activities are, and who will be responsible for conducting them as data ownership and access security will be different in the production systems compared to test systems.
Post Go-Live Considerations
Performance issues.
  Backlog of business – impact on batch process - plan starts to throttle.
  Test the day in a life scenario with full- or almost full-scale
User adoption and Feedback channels
  People that finds workaround on things that they don't really understand – consider implications
  Adoption / change management is the key as harder to communicate as colleagues
  Prepare people to rase issues and give them tools to collaborate – eg Teams or Yarmmer channels
  In the first few weeks of Go Live the rate of business might slow as users develop expertise in the new system– ensure stakeholder support
  Tighter connected departments, functional areas and processes – harder with a new system
  Champions in each department can help – enthusiasm is contagious as rejection
  In remote context, can be useful planning for user sessions, surgery hours and let the users express their issues and doubts.
Date migration can show issues after two/three weeks, so need to consider how long the cutover team will need to be active to support post Go-Live.
  Full business transaction lifecycle process testing on migrated data can help reduce the risk.

## Slide 26: Q/A & Next Steps

## Slide 27: Q&A
Brief Q&A to discuss any additional topic areas.
List questions and follow up actions
Customer slide (please update)

## Slide 28: Next Steps
Discuss next steps and action items.
List next steps and action items
Customer slide (please update)
Notes: Post Go-Live Considerations
Performance issues.
  Backlog of business – impact on batch process - plan starts to throttle.
  Test the day in a life scenario with full- or almost full-scale
User adoption and Feedback channels
  People that finds workaround on things that they don't really understand - implications
  Adoption / change management is the key as harder to communicate as colleagues.
  Prepare people to rase issues and give them tools to collaborate – eg Teams channels
  First weeks the rate of business might slow – ensure stakeholder support
  Tighter connected departments, functional areas and processes – harder with a new system
  Champions in each department can help – enthusiasm is contagious as rejection
  In remote context, can be useful planning for user sessions, surgery hours and let the users express their issues and doubts.
Date migration can show issues after two/three weeks
  Full business transaction lifecycle process testing on migrated data can help

## Slide 29
© 2020 Microsoft Corporation. All rights reserved. Microsoft, Microsoft Dynamics, Office 365, Windows, and other product names are or may be registered trademarks and/or trademarks in the U.S. and/or other countries. The information herein is for informational purposes only and represents the current view of Microsoft Corporation as of the date of this presentation. Because Microsoft must respond to changing market conditions, it should not be interpreted to be a commitment on the part of Microsoft, and Microsoft cannot guarantee the accuracy of any information provided after the date of this presentation. MICROSOFT MAKES NO WARRANTIES, EXPRESS, IMPLIED OR STATUTORY, AS TO THE INFORMATION IN THIS PRESENTATION